Evidence demonstrates that effective staff, patient and public engagement leads to increased patient satisfaction, more positive outcomes and improved relationships with patients and teams. Therefore the main focus of this communication strategy is engagement with staff members,  patients and public engagement. This will be fundamental to achieving our aim to deliver person-centred, safe and high quality care for mothers and babies throughout pregnancy, birth and following birth.

The purpose of this communication plan is to help inform and integrate all the elements of the Best Start programme1 and its recomendations into our everyday care activities within the Women and Childrens service in NHSGGC. By planning a short, medium and long-term strategy, this will allow us to be more proactive and responsive.

The communication plan will help to deploy resources more effectively and strategically by highlighting synergies and shared opportunities in the various phases of the programme. The creation of this communication plan will focus the mission and vision to implement and embed the recommendations within Best Start report across services and sites in NHSGGC.

Communications Infrastructure

- NHSGGC has a proactive communication team and department their support and input will be essential to reach a wider target audience, such as Scottich Government, partner organisations,patients and to achieve wider public engagement.

- In consultation with the Board Nurse Director (project sponsor) and Chief Midwife (strategic project Board Lead) will monitor the Maternity & Neonatal Review Executive Group management and delivery of the communication plan.

- Communications workload will be delegated to a communications sub group and editorial group.

- Supporting the communications process and message delivery will be NMAHP Directorate,Organisational Development, Pracitce Development, Learning and Education

- Internal Nursing and Midwifery, Allied Health Professional communications will be through the normal governance structures.

- The Best Start - Maternity & Neonatal National Review 2017

Goals

The main goal is to communicate what The Best Start Programme is and what it means for all staff, women, and their families who work and experience our care in NHS GGC. We wish to assure, consult and inform all staff  and convey our key objective goinf forward in the short, medium and longterm is to focus on the individual needs of each and every family, in achieving this aim, we will improve the quality and safety of services and secure improved health and wellbeing for mothers and babies.

Target Audience

All staff, working in partnership with staff side representatives from the point of care to the Health Board, patients,relatives and carers. Utilising differing  modes of communications as is appropriate for each target audience.

Best Start Vision

- All mothers and babies are offered a truly family-centred, safe and compassionate approach to their care, recognising their own unique circumstances and preferences

- Fathers, partners and other family members are actively encouraged and supported to become an integral part of all aspects of maternal and newborn care

- Women experience real continuity of care and carer, across the whole maternity journey, with vulnerable families being offered any additional tailored support they may require

- Services are redesigned using the best available evidence, to ensure optimal outcomes and sustainability, and maximise the opportunity to support normal birth processes and avoid unnecessary interventions

- Staff are empathetic, skilled and well supported to deliver high quality, safe services, every time

- Multi-professional team working is the norm within an open and honest team culture, with everyone’s contribution being equally valued.

Communications Channels and Outlets

Key communications channels :

- Reference groups

- Professional fora

- Organisational and partnership structures

- Patient and partnerships fora

- NHS GGC existing communication systems (core brief, team brief, Staff News, Staff Net, Nursing and Midwifery section on NHSGGC website)

- Nursing and Midwifery and Allied Health Professional governance structures.

- Intranet, Internet, Social media (Twitter, U-Tube)

- Information posters

The target audience/s will be reached using the above modes of communication with the support of  the Best Start Project Team, Board Nurse Director, Chief Midwife, Senior Sector Multidisciplinary Team and the Chief Nurse Governance and Regulation.

Communications Support

NHS GGC commincations team will provide expert support with all media releases, social media and staff communications.

Tracking and Evaluation

A variety of methods/groups  will be utilised to track communications with the target audience/s. Data will be collected using a bespoke questionnaires or incorporating Best Start questions currently in use within questionnaires, staff and patient stories

- Consult with the SCN/M/TL Virtual reference groups

- All  levels of MDT staff focus groups

- Staff feedback via the Nursing and Midwifery NHSGGC staff net.

- GGC patient engagment department will engage with the wider community.

Best Start Communication Plan

| Comms Product | Stakeholder Group(s) / Audience | Purpose (impact addressed) / Effect | Key Message | Channel | Frequency | Approval level required | Start date | End date | Owner |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| National Best Start Powerpoint presentation | All Staff within Maternity & Neonatal service Staff partnerships | All staff awareness of the Best Start programme & benefits | Are You Ready to change ! | Distributed by Ass Chief N/M Gov & Regulation Availalble on internet & staff net site | On going | Maternity & Neonatal Review Executive Group | Oct’17 |  | Chief Midwife Lead Obst’ |
| Road Show Information Posters | All staff, | Invite all staff to attend staff awareness, information and consultation of the Best Start programme | What is Best Start and where to get more info | Staff areas changing rooms offices, e-mail Core brief Intranet Best Start Button on staff net | 2 weeks Prior to Roadshow schedule | Chief Midwife | Nov’17 | Jan18 | CM & Lead Obst’ |
| All Staff Road Show Information Sessions | All Staff within Maternity & Neonatal service Staff partnerships | Introduce the Best Start project. | We need your support | All of the above & Individual MDT Governance Meeting Agendas | Daily 12-2 pm sessions over 1 week duration Info session with/ facilitated feedback Repeat format with new info at intervals as required through the project | Maternity & Neonatal Review Executive Group | Nov’17 | End Jan 18 | Chief Midwife Lead Obst’ O Dev’ Staff Side |
| Nursing and Midwifery Portal (N&MP) Internet | All Staff within Maternity & Neonatal Service Staff partnerships Public | To let them know about Best Start programme. Benefits/ Implications for patients and staff | Best Start programme will develop the future vision of care for the maternity and neonatal services across Scotland | Intranet | Ongoing | Chief Midwife Ass CN/M Gov & Regulation | Nov 17 |  | EF/AC |
| Best Start Staff net | All Staff within Maternity & Neonatal Service Staff partnerships | Mulitpurpose ways to support effective communication & consultation Sign post to FAQ’S Programme Suggestions Forum Rumour Buster Platform | We are listening and working with you | Staffnet | Ongoing | Board Nurse Director Chief Midwife Board Communication Team Organisational Development Mananger | Dec’17 |  | Chief Midwife, OD and Staff Side |
| Staff Newsletter | All Staff within Maternity & Neonatal Service Staff partnerships | To provide all staff with accurate & regular programme information & developments National Progress Updates included | We want to keep you informed of changes and progress | Staff areas changing rooms offices, e-mail Team brief Intranet Best Start Button on staff net Individual MDT Governance Meeting Agendas | On going | Maternity & Neonatal Review Executive Group | Jan 18 |  | Editorial sub group members |
| Generic Information Posters | All staff, Women & their families Staff partnerships General Public | Preparation for pilot projects implementation in some areas across the womens service in NHS GGC In particular: Clyde Project MLU’s – QEUH & PRM New Transisitional Care arrangements | Working on improvements to our service and keeping you informed of our progress | Staff & patient areas offices intranet e-mail Core brief Staff net news banner | Prior to Early Implementor work starting | Maternity & Neonatal Review Executive Group | Feb’18 |  | Chief Midwife, Com’s Team, OD |
| Early Implmentor progress Reports | Scottish Government NHS GGC Board All staff Staff partnerships | Progress of actions completed, risks/benefits any slippage | Keeping you informed of our testing work | Briefing Papers Reports Staff net N/Letter Governance Meeting Notes | On going | Maternity & Neonatal Review Executive Group |  |  | Chief Midwife, Ass CN/M |
| NHS GGC Maternity & Neonatal Review Executive Group | NHS GGC Board Acute Services Committee Clinical & Care Governance Committee Area Partnership Forum | Inform of programme actions, plans and progress | Care Assurance & Programme Progress | Briefing Papers Reports Staff Net Intranet Governance meeting notes Power Point Presentations | On going | Board Nurse Director | Dec ‘17 |  | Chief Midwife Members of the Maternity & Neonatal Review Executive Group |
| NHSGGC Midwifery Birthing Units Early Alert Information | Scottish Government NHSGGC Communications team | Provide Scottish Government & local com’s team with advanced notice of local NHSGGC improvement work/changes pertinent to the midwifery stand alone birthing units of VOL & IRH To inform for National/Local Press focus | Appraising of changes | Briefing Email | On going | Board Nurse Director Chief Executive | Jan 18 |  | Chief Midwife Members of the Maternity & Neonatal Review Executive Group |